## 00 - START HERE
The Delivery Credibility Gap
IT Delivery Control Toolkit. Karim Gaber Saleh.
Start here
Use the registers to prepare the next useful decision. The dashboard keeps condition, trajectory and evidence confidence separate.
Weekly workflow: configure settings, update records, review controls, inspect attention items, agree interventions, take steering decisions, then test their effects.
Inputs are pale cream. Calculated cells are pale mint. Filter the registers by ID, owner or flag. The first two columns and headers stay visible while you scroll.
Control | Question
Value | Is this still worth doing?
Flow | Can useful work move?
Dependencies | What prevents independent progress?
Decisions | Are necessary decisions timely?
Assurance | What evidence supports the claim?
Readiness | Can operations safely run this?
Adoption | Is use contributing to the outcome?
Condition: Within tolerance, Watch, Intervention required, Unknown. Trajectory: Improving, Stable, Deteriorating, Unclear. Confidence: High, Medium, Low.
Flags are local rule-based attention prompts. They neither predict project success nor accept risk. Do not average the Seven Controls or treat the evidence domains as a score. Mandatory governance still applies.
Atlas is fictional. Role labels, dates and supporting extensions illustrate use. DEP-07 is due 25 Sep and is not yet overdue at the 24 Sep review, despite two earlier missed commitments.
Navigation
01 - PROJECT SETUP
02 - CONTROL DASHBOARD
03 - HEALTH REVIEW
04 - DECISION LOG
05 - DEPENDENCIES
06 - FLOW
07 - EVIDENCE & ASSURANCE
08 - READINESS
09 - ADOPTION & BENEFITS
10 - RECOVERY
11 - STEERING PACK
12 - NEXT ACTIONS
13 - DATA & LISTS
14 - REVIEW HISTORY
15 - AI DELEGATION
Start a clean project
Save a new copy. On each register, select the named Clear_ range using the Name Box and press Delete. Clear only contents. Keep IDs H-01 to H-07, control labels and readiness area names.
Clear_Steering and Clear_History remove the example meeting and snapshots. Replace Project Setup values and review dates. Blank readiness rows remain unassessed. Re-enter unique IDs to activate records.
Capacity: 50 records per working register, seven current controls and 100 history rows. Use the prepared blank rows. Adding rows outside these ranges requires extending formulas, validations, names and the action pool.
Before each review, save a value-only dated snapshot on Review History. Update Previous review date and Review date on Project Setup. Formula-based history would change retrospectively.
Qualification: retain the entered judgement and record context in Health Review Notes. Automated flags remain visible until the source facts change. Risk acceptance belongs to the authorised decision maker.
Print Dashboard or Steering Pack for discussion. Wide source registers are operational records. Print a selected column group at readable scale rather than shrinking the entire register.
Sources and field mappings are on Data & Lists. This workbook contains no macros and sends no data externally.

## 01 - PROJECT SETUP
Project setup
Illustrative Atlas settings. Replace local thresholds and owners before using the workbook on a live project.
Start here
Setting | Value | Definition / local rule
Project name | Atlas migration | Fictional worked example
Programme / portfolio | Enterprise migration
PM | Programme manager | Role labels are illustrative, not named people
Sponsor | Sponsor
Business owner | Operations director
Service owner | Service owner
Review date | 2026-09-24 | Fixed as-of date. Update for each review.
Review horizon (days) | 14 | Window for upcoming commitments
Next major commitment | 2026-09-30 | Illustrative release hold point, subject to evidence
Currency | EUR | Used only for locally entered financial measures
Reporting cadence | Weekly
Current phase | Pilot validation
Context | Smaller wave or defer full release | Do not shorten required testing
Decision warning days | 7 | Calendar days since actionable date
Decision escalation days | 14 | Calendar days since actionable date
Missed commitments threshold | 2 | Flag when commitments missed reaches this value
Blocker age threshold | 5 | Calendar days waiting while blocked
Milestone movement threshold | 2 | Flag repeated movements at or above this count
Evidence freshness days | 30 | Local maximum age without an explicit expiry
Benefits observation days | 30 | Local observation period reminder
Review cadence days | 7 | Reminder only. Save history manually before updating
Upcoming window days | 14 | Dashboard deadline window
Previous review date | 2026-09-17 | Must match a saved date in Review History
Local settings are practitioner conventions, not industry benchmarks. Calendar-day calculations preserve pauses and deferrals.
Local settings entered

## 02 - CONTROL DASHBOARD
Control dashboard
Review judgement beside the underlying triggers. No overall score. Empty registers mean no assessment, not proven health.
Start here
Control | Condition | Trajectory | Confidence | Key signal / issue | Next action | Owner | Due date | Attention | Records needing attention
Value | Within tolerance | Stable | Medium | Need reconfirmed 22 Sep; remaining cost open (24 Sep 2026) | Validate remaining cost | Sponsor | 2026-09-28 |  | 0
Flow | Watch | Deteriorating | High | Acceptance queue growing across reviews (24 Sep 2026) | Limit new starts | Delivery lead | 2026-09-25 |  | 1
Dependencies | Intervention required | Deteriorating | High | DEP-07 missed two commitments (24 Sep 2026) | Agree alternative sequence | Network owner | 2026-09-25 | INTERVENTION REQUIRED | 2
Decisions | Intervention required | Deteriorating | High | D-014 actionable since 6 Sep (24 Sep 2026) | Select release option | Sponsor | 2026-09-25 | INTERVENTION REQUIRED | 2
Assurance | Unknown | Unclear | Low | Production-scale recovery not demonstrated (24 Sep 2026) | Commission representative rehearsal | Assurance lead | 2026-09-29 | EVIDENCE GAP BEFORE COMMITMENT | 2
Readiness | Watch | Stable | Medium | On-call access unverified (24 Sep 2026) | Rehearse operator access | Service owner | 2026-09-28 |  | 9
Adoption | Watch | Unclear | Low | Eligible-user denominator missing (24 Sep 2026) | Establish cohort | Business owner | 2026-09-30 |  | 1
Critical attention. Highest-priority open items. The complete queue is on Next Actions.
Source ID | Issue | Owner | Due date | Consequence | Next action
H-03 | DEP-07 missed two commitments | Network owner | 2026-09-25 | Release or outcome claim remains constrained | Agree alternative sequence |  |  |  |  | 3
H-04 | D-014 actionable since 6 Sep | Sponsor | 2026-09-25 | Release or outcome claim remains constrained | Select release option |  |  |  |  | 4
D-014 | Full release or smaller migration wave | Sponsor | 2026-09-25 | Cutover booking and supplier slot exposed | Escalate to named authority. Preserve original actionable date. |  |  |  |  | 8
DEP-07 | Cloud pilot network connectivity | Network owner | 2026-09-25 | Pilot production path cannot be accepted | Review eliminate / decouple options before accepting another forecast. |  |  |  |  | 58
R-04 | Access and on-call readiness | Access owner | 2026-09-28 | Operators cannot demonstrate privileged access | Hold release or obtain explicit authorised risk acceptance. |  |  |  |  | 211
Next consequential decision. Sponsor or steering authority.
Decision ID | Decision required | Owner | Deadline | Consequence of delay | Evidence required
D-014 | Full release or smaller migration wave | Sponsor | 2026-09-25 | Cutover booking and supplier slot exposed | Accepted connectivity and representative recovery evidence |  |  |  |  | 8
Evidence gaps. Review the claim and its permitted scope.
Source ID | Claim / issue | Evidence challenge | Next action | Owner | Due date
H-05 | Production-scale recovery not demonstrated | EVIDENCE GAP BEFORE COMMITMENT | Commission representative rehearsal | Assurance lead | 2026-09-29 |  |  |  |  | 5
CAP-01 | Atlas pilot recovery / release candidate 3 | REPRESENTATIVE CAPABILITY NOT VERIFIED | Commission targeted evidence before the commitment date. | Assurance lead | 2026-09-29 |  |  |  |  | 158
B-01 | Reduce manual recovery coordination | DENOMINATOR MISSING OR ZERO NO BASELINE HANDOVER NOT RECORDED | Define eligible cohort before reporting adoption percentage. | Service owner | 2026-09-29 |  |  |  |  | 258
H-07 | Eligible-user denominator missing |  | Establish cohort | Business owner | 2026-09-30 |  |  |  |  | 7
Readiness blockers. Recorded risk acceptance does not automatically clear a blocker.
Source ID | Requirement | Trigger | Next action | Owner | Due date
R-04 | Access and on-call readiness | RELEASE BLOCKER LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Access owner | 2026-09-28 |  |  |  |  | 211
R-05 | Recovery and data integrity | RELEASE BLOCKER READINESS UNKNOWN LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Assurance lead | 2026-09-29 |  |  |  |  | 212
R-11 | Cutover | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 |  |  |  |  | 218
R-12 | Rollback | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 |  |  |  |  | 219
Upcoming deadlines within the configured window.
Source ID | Issue | Owner | Deadline | Consequence | Next action
H-02 | Acceptance queue growing across reviews | Delivery lead | 2026-09-25 | Release or outcome claim remains constrained | Limit new starts |  |  |  |  | 2
H-03 | DEP-07 missed two commitments | Network owner | 2026-09-25 | Release or outcome claim remains constrained | Agree alternative sequence |  |  |  |  | 3
H-04 | D-014 actionable since 6 Sep | Sponsor | 2026-09-25 | Release or outcome claim remains constrained | Select release option |  |  |  |  | 4
D-014 | Full release or smaller migration wave | Sponsor | 2026-09-25 | Cutover booking and supplier slot exposed | Escalate to named authority. Preserve original actionable date. |  |  |  |  | 8
DEP-07 | Cloud pilot network connectivity | Network owner | 2026-09-25 | Pilot production path cannot be accepted | Review eliminate / decouple options before accepting another forecast. |  |  |  |  | 58
All action records: 22. Critical: 10. Readiness blockers: 4

## 03 - HEALTH REVIEW
Seven Controls health review
Three separate judgements. High confidence needs current, relevant, corroborated support. Medium is partial. Low is weak, stale or conflicting.
Start here | [9 empty] | Rows missing an ID: 0
ID | Control | Condition | Trajectory | Confidence | Flags | Intervention | Owner | Due date | Confidence reason | Dated signal | Primary issue | Consequence | Evidence reference | Notes | Priority | Suggested action
H-01 | Value | Within tolerance | Stable | Medium |  | Validate remaining cost | Sponsor | 2026-09-28 | Need reconfirmed 22 Sep; remaining cost open | Need reconfirmed 22 Sep; remaining cost open (24 Sep 2026) | Need reconfirmed 22 Sep; remaining cost open | Continuing value not fully evidenced | Atlas review 24 Sep |  | Routine | Validate remaining cost
H-02 | Flow | Watch | Deteriorating | High |  | Limit new starts | Delivery lead | 2026-09-25 | Acceptance queue growing across reviews | Acceptance queue growing across reviews (24 Sep 2026) | Acceptance queue growing across reviews | Release or outcome claim remains constrained | Atlas review 24 Sep |  | Routine | Limit new starts
H-03 | Dependencies | Intervention required | Deteriorating | High | INTERVENTION REQUIRED | Agree alternative sequence | Network owner | 2026-09-25 | DEP-07 missed two commitments | DEP-07 missed two commitments (24 Sep 2026) | DEP-07 missed two commitments | Release or outcome claim remains constrained | DEP-07 |  | Critical | Agree alternative sequence
H-04 | Decisions | Intervention required | Deteriorating | High | INTERVENTION REQUIRED | Select release option | Sponsor | 2026-09-25 | D-014 actionable since 6 Sep | D-014 actionable since 6 Sep (24 Sep 2026) | D-014 actionable since 6 Sep | Release or outcome claim remains constrained | D-014 |  | Critical | Select release option
H-05 | Assurance | Unknown | Unclear | Low | EVIDENCE GAP BEFORE COMMITMENT | Commission representative rehearsal | Assurance lead | 2026-09-29 | Production-scale recovery not demonstrated | Production-scale recovery not demonstrated (24 Sep 2026) | Production-scale recovery not demonstrated | Release or outcome claim remains constrained | CAP-01 |  | Critical | Commission representative rehearsal
H-06 | Readiness | Watch | Stable | Medium |  | Rehearse operator access | Service owner | 2026-09-28 | On-call access unverified | On-call access unverified (24 Sep 2026) | On-call access unverified | Release or outcome claim remains constrained | R-04 |  | Routine | Rehearse operator access
H-07 | Adoption | Watch | Unclear | Low |  | Establish cohort | Business owner | 2026-09-30 | Eligible-user denominator missing | Eligible-user denominator missing (24 Sep 2026) | Eligible-user denominator missing | Release or outcome claim remains constrained | Atlas review 24 Sep |  | Routine | Establish cohort

## 04 - DECISION LOG
Decision latency log
Keep the original actionable date through deferrals. Decision, implementation and effect are separate. Dates use calendar days.
Start here |  | Open decisions: 1. Oldest actionable age: 18 days. Overdue: 0 | [7 empty] | Rows missing an ID: 0
ID | Decision required | Status | Owner | Required by | Priority | Flags | Suggested action | Consequence | Evidence required | Category | First raised date | Actionable date | Actionable criteria | Authority | Options | Recommendation | Escalation trigger | Escalation route | Pauses / deferrals | Deferrals count | Next review | Decision | Rationale | Decision date | Implementer | Communication status | Effect check | Linked dependency | Linked milestone | Linked readiness | Implementation due | Implemented on | Open age | Closed latency | Days until due | Days overdue | Implementation lag | Dependency state
D-014 | Full release or smaller migration wave | Open | Sponsor | 2026-09-25 | Critical | THRESHOLD EXCEEDED ESCALATION REQUIRED APPROACHING DEADLINE LINKED DEPENDENCY UNRESOLVED | Escalate to named authority. Preserve original actionable date. | Cutover booking and supplier slot exposed | Accepted connectivity and representative recovery evidence | Release scope | 2026-09-01 | 2026-09-06 | Cost, exposure and two options presented | Sponsor | Smaller wave on existing connection, or defer full wave | Smaller wave subject to recovery test | No substantive choice by 25 Sep noon | Programme board chair | 18 Sep discussion deferred pending sponsor availability. No days excluded. | 1 | 2026-09-25 |  |  |  | Programme manager | Pending decision | Verify revised acceptance path at next review | DEP-07 | M-01 | R-04 | 2026-09-26 |  | 18 |  | 1 | 0 |  | Unresolved

## 05 - DEPENDENCIES
Dependency engineering
Eliminate, decouple, contract and control are options. Closure needs consumer-accepted evidence or authorised removal. Provider completion alone is insufficient.
Start here | [9 empty] | Rows missing an ID: 0
ID | Dependency | Status | Owner | Required by | Priority | Flags | Suggested action | Consequence | Next evidence | Value path / milestone | Provider | Consumer | Shared owner | Criticality | Forecast date | Forecast confidence | Commitments missed | Eliminate option | Decouple option | Interface / contract | Acceptance evidence | Consumer accepted | Accepted date | Change-notification rule | Control signal | Escalation rule | Fallback | Residual coupling | Approval required | Due date | Removal authorised | Removal authority | Removal evidence | Closure basis | Days until due | Days overdue
DEP-07 | Cloud pilot network connectivity | In progress | Network owner | 2026-09-25 | Critical | REPEATED MISSED COMMITMENT LOW-CONFIDENCE FORECAST CONSUMER ACCEPTANCE MISSING | Review eliminate / decouple options before accepting another forecast. | Pilot production path cannot be accepted | Consumer witnesses production-path test | M-01 | Network supplier | Migration team | Network service owner | Critical | 2026-09-25 | Low | 2 | Production routing required for live pilot | Lab route for preliminary tests only | Routing specification v3. Throughput, failover and access tests |  | No |  | Notify forecast change immediately | Inspect accepted evidence daily | Escalate missed commitment | Reduce wave or defer | Production path still needs acceptance | Sponsor approves sequence | 2026-09-25 | No |  |  | Unresolved | 1 | 0

## 06 - FLOW
Flow and feedback
Track the waiting between assumption and evidence. Throughput alone is not the objective. Use comparable slices and preserve acceptance quality.
Start here |  | WIP: 1. Acceptance queue: 1. Rework occurrences: 1 | [7 empty] | Rows missing an ID: 0
ID | Work item / slice | Stage | Owner | Due date | Priority | Flags | Suggested action | Consequence | Next evidence | Start date | Waiting start | Acceptance date | Blocked | Blocker reason | Rework count | Handoff count | Acceptance owner | Linked milestone | Milestone movements | Previous blocker age | Blocker age | Waiting days | WIP | Acceptance queue | Blocker trend
F-01 | Production-path acceptance | Acceptance queue | Network owner | 2026-09-25 | Review | BLOCKER AGE THRESHOLD REPEATED MILESTONE MOVEMENT | Resolve the constraint and shorten the next evidence loop. | Release evidence remains unavailable | Witnessed routing and failover tests | 2026-09-10 | 2026-09-18 |  | Yes | DEP-07 connectivity acceptance | 1 | 3 | Migration lead | M-01 | 2 | 0 | 6 | 6 | 1 | 1 | Growing

## 07 - EVIDENCE & ASSURANCE
Evidence and assurance
Six distinct claim domains, not a maturity score. Adoption does not prove safety. Every positive claim needs its own conditions and evidence.
Start here | [9 empty] | Rows missing an ID: 0
ID | Capability / version | Status | Owner | Due date | Priority | Flags | Suggested action | Consequence | Next evidence | Decision supported | Activity claim | Output claim | Verified capability claim | Readiness claim | Adoption claim | Realised-value claim | Test conditions | Acceptance criteria | Result | Reviewer | Evidence location | Evidence date | Expiry date | Assumptions | Exceptions | Invalidation trigger | Required for commitment | Readiness basis | Benefit baseline | Attribution caveat | Readiness asserted | Benefit asserted | Fresh until
CAP-01 | Atlas pilot recovery / release candidate 3 | In progress | Assurance lead | 2026-09-29 | Critical | REPRESENTATIVE CAPABILITY NOT VERIFIED | Commission targeted evidence before the commitment date. | Release recovery claim unsupported at production scale | Production-path rehearsal with receiving operator | D-014 | Lab exercise executed 22 Sep | Recovery procedure v3 exists | Lab objectives met. Production-scale result unknown | Operator access and out-of-hours escalation not demonstrated | No normal-duty use claim | No measured resilience benefit claimed | Lab differs from production volume and interfaces | Agreed recovery objectives under representative production conditions | Lab only | Assurance lead | Atlas lab exercise log 22 Sep (illustrative reference) | 2026-09-22 |  | Production data volume remains untested | Lab result cannot substitute for production test | Interface or data-volume change | Yes | Technical test only |  |  | No | No | 2026-10-22
Formulas:
Fresh until = IF([ID]="","",IF(ISNUMBER([Expiry date]),[Expiry date],IF(ISNUMBER([Evidence date]),[Evidence date]+FreshDays,"")))

## 08 - READINESS
Day-1 readiness
A single release blocker remains visible. A named authority alone is not risk acceptance. Record decision evidence and expiry. The workbook never authorises release.
Start here |  | Passed: 3. Gaps: 1. Unknown: 8. Active release blockers: 4 | [7 empty] | Rows missing an ID: 0
ID | Area / requirement | Assessment | Owner | Due date | Priority | Flags | Suggested action | Release consequence | Evidence | Result | Criticality | Release blocker | Risk authority | Exception expiry | Risk acceptance record | Evidence date | Evidence expiry | Linked dependency | Linked decision | NA reason | Active blocker | Exception state | Dependency state
R-01 | Service ownership | Pass | Service owner | 2026-09-28 | Routine |  |  | Receiving team needs operational evidence | Scope and boundaries accepted | Demonstrated | High | No |  |  |  | 2026-09-22 |  |  | D-014 |  | No | No acceptance recorded
R-02 | Observability | Unknown | Service owner | 2026-09-28 | Review | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Receiving team needs operational evidence |  | Evidence pending | High | No | [6 empty] | D-014 |  | No | No acceptance recorded
R-03 | Support and service desk | Pass | Service owner | 2026-09-28 | Routine |  |  | Receiving team needs operational evidence | Representative ticket routing tested | Demonstrated | High | No |  |  |  | 2026-09-23 |  |  | D-014 |  | No | No acceptance recorded
R-04 | Access and on-call readiness | Gap | Access owner | 2026-09-28 | Critical | RELEASE BLOCKER LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Operators cannot demonstrate privileged access |  | Evidence pending | Critical | Yes | [5 empty] | DEP-07 | D-014 |  | Yes | No acceptance recorded | Unresolved
R-05 | Recovery and data integrity | Unknown | Assurance lead | 2026-09-29 | Critical | RELEASE BLOCKER READINESS UNKNOWN LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Recovery at production scale not demonstrated |  | Evidence pending | Critical | Yes | [5 empty] | DEP-07 | D-014 |  | Yes | No acceptance recorded | Unresolved
R-06 | Security | Unknown | Service owner | 2026-09-28 | Review | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Receiving team needs operational evidence |  | Evidence pending | High | No | [6 empty] | D-014 |  | No | No acceptance recorded
R-07 | Documentation | Unknown | Service owner | 2026-09-28 | Review | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Receiving team needs operational evidence |  | Evidence pending | High | No | [6 empty] | D-014 |  | No | No acceptance recorded
R-08 | Supplier support | Pass | Service owner | 2026-09-28 | Routine |  |  | Receiving team needs operational evidence | Support hours and escalation confirmed | Demonstrated | High | No |  |  |  | 2026-09-23 |  |  | D-014 |  | No | No acceptance recorded
R-09 | Training | Unknown | Service owner | 2026-09-28 | Review | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Receiving team needs operational evidence |  | Evidence pending | High | No | [6 empty] | D-014 |  | No | No acceptance recorded
R-10 | Incident response | Unknown | Service owner | 2026-09-29 | Review | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Receiving team needs operational evidence |  | Evidence pending | High | No | [6 empty] | D-014 |  | No | No acceptance recorded
R-11 | Cutover | Unknown | Service owner | 2026-09-29 | Critical | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Receiving team needs operational evidence |  | Evidence pending | Critical | Yes | [6 empty] | D-014 |  | Yes | No acceptance recorded
R-12 | Rollback | Unknown | Service owner | 2026-09-29 | Critical | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Receiving team needs operational evidence |  | Evidence pending | Critical | Yes | [6 empty] | D-014 |  | Yes | No acceptance recorded

## 09 - ADOPTION & BENEFITS
Adoption and benefits
Usage alone is not benefit. Keep the eligible cohort, outcome baseline, balancing measure and alternative explanations visible.
Start here | [9 empty] | Rows missing an ID: 0
ID | Outcome | Status | Owner | Due date | Priority | Flags | Suggested action | Consequence | Evidence required | Business owner | Capability | Required behaviour | Cohort | Eligible denominator | Actual numerator | Adoption rate | Baseline | Target | Observation start | Observation end | Current result | Source | Balancing measure | External influences | Attribution limit | Intervention | Benefits handover | Next review | Baseline date | Target date | Adoption direction | Outcome direction | Observation days
B-01 | Reduce manual recovery coordination | In progress | Service owner | 2026-09-29 | Review | DENOMINATOR MISSING OR ZERO NO BASELINE HANDOVER NOT RECORDED | Define eligible cohort before reporting adoption percentage. | Outcome claim cannot yet be supported | Comparable operator-led exercise with defined eligible cohort | Operations director | CAP-01 | Use approved runbook and escalation path | Eligible operators and exercises to be defined | [7 empty] | One lab exercise. Outcome evidence insufficient | Atlas lab exercise 22 Sep | Recovery accuracy, data integrity and operator effort | Exercise difficulty and staffing vary | Cannot attribute change solely to platform | Run comparable operator-led exercise | No | 2026-09-30 |  |  | Unknown | Unknown

## 10 - RECOVERY
RESET recovery review
Recognise. Establish Reality. Surface Causes. Execute Interventions. Test Recovery. The 72-hour review is an initial focus period, not a recovery guarantee.
Start here | [9 empty] | Rows missing an ID: 0
ID | Recovery trigger | RESET stage | Owner | Due date | Priority | Flags | Suggested action | Exposure | Evidence required | Mandate | Scope | Authority | Accepted work | Evidence | Remaining work | Suspected cause | Alternative explanation | Test of explanation | Options | Recommendation | Sequence | Recovery test | Observation date | Unknowns | Investigation owner | Sponsor decision | Next review | Intervention effect | Effect evidence | Decision latency change | Dependency acceptance change | Blocker age change | Evidence availability change | Readiness change | Forecast credibility change | Displaced risk | Status | Linked decision | Linked dependency
REC-01 | Connectivity and decision deterioration | Establish Reality | Programme manager | 2026-09-26 | Routine |  | Test the intervention, sustained change and displaced risk. | Cutover slot and remaining cost exposure | Accepted production path and operator-led rehearsal | Initial Atlas review 24-26 Sep | Release sequence and evidence gaps | Sponsor authorises evidence access and option preparation | Pilot build and lab recovery | CAP-01 lab log | Connectivity, access and representative recovery | Shared decision ownership and uncertain sequence | Technical routing defect | Inspect failure and supplier acceptance records | Reduce first wave or defer | Smaller wave only if acceptance criteria met | Sponsor scope choice, interface acceptance, operator rehearsal | Accepted production path and receiving-operator rehearsal | 2026-09-30 | Remaining cost range | Commercial lead | Pending D-014 | 2026-09-30 | Extra build capacity did not reduce acceptance waiting | Illustrative review observation, not recovery proof | Baseline 18 days open on 24 Sep | DEP-07 still unaccepted | F-01 waiting 6 days | Production-scale test outstanding | R-04 access remains unverified | Low after two missed commitments | Check revalidation load if wave reduced | In progress | D-014 | DEP-07

## 11 - STEERING PACK
Steering pack
Decision pre-read and meeting record. Keep unresolved evidence and dissent visible. Source registers own the facts.
Start here
Value movement
Need reconfirmed 22 Sep; remaining cost open (24 Sep 2026). Next action: Validate remaining cost
Control | Previous trajectory | Current trajectory | Change | Intervention | Owner | Due date
Value | Stable | Stable | Unchanged | Validate remaining cost | Sponsor | 2026-09-28
Flow | Deteriorating | Deteriorating | Unchanged | Limit new starts | Delivery lead | 2026-09-25
Dependencies | Stable | Deteriorating | Changed | Agree alternative sequence | Network owner | 2026-09-25
Decisions | Stable | Deteriorating | Changed | Select release option | Sponsor | 2026-09-25
Assurance | Stable | Unclear | Changed | Commission representative rehearsal | Assurance lead | 2026-09-29
Readiness | Stable | Stable | Unchanged | Rehearse operator access | Service owner | 2026-09-28
Adoption | Stable | Unclear | Changed | Establish cohort | Business owner | 2026-09-30
Decisions requiring sponsor or steering authority
Source ID | Issue | Trigger | Action prompt | Owner | Due date
D-014 | Full release or smaller migration wave | THRESHOLD EXCEEDED ESCALATION REQUIRED APPROACHING DEADLINE LINKED DEPENDENCY UNRESOLVED | Escalate to named authority. Preserve original actionable date. | Sponsor | 2026-09-25 |  |  | 8
0
0
Critical dependencies
Source ID | Issue | Trigger | Action prompt | Owner | Due date
DEP-07 | Cloud pilot network connectivity | REPEATED MISSED COMMITMENT LOW-CONFIDENCE FORECAST CONSUMER ACCEPTANCE MISSING | Review eliminate / decouple options before accepting another forecast. | Network owner | 2026-09-25 |  |  | 58
0
0
Evidence gaps
Source ID | Issue | Trigger | Action prompt | Owner | Due date
H-05 | Production-scale recovery not demonstrated | EVIDENCE GAP BEFORE COMMITMENT | Commission representative rehearsal | Assurance lead | 2026-09-29 |  |  | 5
CAP-01 | Atlas pilot recovery / release candidate 3 | REPRESENTATIVE CAPABILITY NOT VERIFIED | Commission targeted evidence before the commitment date. | Assurance lead | 2026-09-29 |  |  | 158
B-01 | Reduce manual recovery coordination | DENOMINATOR MISSING OR ZERO NO BASELINE HANDOVER NOT RECORDED | Define eligible cohort before reporting adoption percentage. | Service owner | 2026-09-29 |  |  | 258
Readiness threats
Source ID | Issue | Trigger | Action prompt | Owner | Due date
R-04 | Access and on-call readiness | RELEASE BLOCKER LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Access owner | 2026-09-28 |  |  | 211
R-05 | Recovery and data integrity | RELEASE BLOCKER READINESS UNKNOWN LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Assurance lead | 2026-09-29 |  |  | 212
R-11 | Cutover | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 |  |  | 218
Previous intervention effects
Extra build capacity did not reduce acceptance waiting. Evidence: Illustrative review observation, not recovery proof
Decision record. Transfer an agreed decision and date to the owning Decision Log record.
Decision ID | Decision | Rationale | Dissent | Conditions | Implementer | Communication | Meeting date
Formulas:
Due date = IF(COUNTIF('03 - HEALTH REVIEW'!$B9:B15,[Control])<>1,"",IF(INDEX('03 - HEALTH REVIEW'!$I9:I15,MATCH([Control],'03 - HEALTH REVIEW'!$B9:B15,0))="","",INDEX('03 - HEALTH REVIEW'!$I9:I15,MATCH([Control],'03 - HEALTH REVIEW'!$B9:B15,0))))

## 12 - NEXT ACTIONS
Next actions
Calculated prompts ordered by Critical, Review, Routine, then due date. This is an attention queue, not a project score. Edit the source record, not this view.
Start here
Priority | Source control | Source ID | Issue | Trigger | Recommended next action | Owner | Due date | Consequence | Evidence required | Status
Critical | Dependencies | H-03 | DEP-07 missed two commitments | INTERVENTION REQUIRED | Agree alternative sequence | Network owner | 2026-09-25 | Release or outcome claim remains constrained | DEP-07 | Intervention required | 3
Critical | Decisions | H-04 | D-014 actionable since 6 Sep | INTERVENTION REQUIRED | Select release option | Sponsor | 2026-09-25 | Release or outcome claim remains constrained | D-014 | Intervention required | 4
Critical | Decisions | D-014 | Full release or smaller migration wave | THRESHOLD EXCEEDED ESCALATION REQUIRED APPROACHING DEADLINE LINKED DEPENDENCY UNRESOLVED | Escalate to named authority. Preserve original actionable date. | Sponsor | 2026-09-25 | Cutover booking and supplier slot exposed | Accepted connectivity and representative recovery evidence | Open | 8
Critical | Dependencies | DEP-07 | Cloud pilot network connectivity | REPEATED MISSED COMMITMENT LOW-CONFIDENCE FORECAST CONSUMER ACCEPTANCE MISSING | Review eliminate / decouple options before accepting another forecast. | Network owner | 2026-09-25 | Pilot production path cannot be accepted | Consumer witnesses production-path test | Unresolved | 58
Critical | Readiness | R-04 | Access and on-call readiness | RELEASE BLOCKER LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Access owner | 2026-09-28 | Operators cannot demonstrate privileged access |  | Gap | 211
Critical | Assurance | H-05 | Production-scale recovery not demonstrated | EVIDENCE GAP BEFORE COMMITMENT | Commission representative rehearsal | Assurance lead | 2026-09-29 | Release or outcome claim remains constrained | CAP-01 | Unknown | 5
Critical | Assurance | CAP-01 | Atlas pilot recovery / release candidate 3 | REPRESENTATIVE CAPABILITY NOT VERIFIED | Commission targeted evidence before the commitment date. | Assurance lead | 2026-09-29 | Release recovery claim unsupported at production scale | Production-path rehearsal with receiving operator | In progress | 158
Critical | Readiness | R-05 | Recovery and data integrity | RELEASE BLOCKER READINESS UNKNOWN LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Assurance lead | 2026-09-29 | Recovery at production scale not demonstrated |  | Unknown | 212
Critical | Readiness | R-11 | Cutover | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 | Receiving team needs operational evidence |  | Unknown | 218
Critical | Readiness | R-12 | Rollback | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 | Receiving team needs operational evidence |  | Unknown | 219
Review | Flow | F-01 | Production-path acceptance | BLOCKER AGE THRESHOLD REPEATED MILESTONE MOVEMENT | Resolve the constraint and shorten the next evidence loop. | Network owner | 2026-09-25 | Release evidence remains unavailable | Witnessed routing and failover tests | Acceptance queue | 108
Review | Readiness | R-02 | Observability | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 209
Review | Readiness | R-06 | Security | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 213
Review | Readiness | R-07 | Documentation | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 214
Review | Readiness | R-09 | Training | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 216
Review | Readiness | R-10 | Incident response | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-29 | Receiving team needs operational evidence |  | Unknown | 217
Review | Adoption | B-01 | Reduce manual recovery coordination | DENOMINATOR MISSING OR ZERO NO BASELINE HANDOVER NOT RECORDED | Define eligible cohort before reporting adoption percentage. | Service owner | 2026-09-29 | Outcome claim cannot yet be supported | Comparable operator-led exercise with defined eligible cohort | In progress | 258
Routine | Flow | H-02 | Acceptance queue growing across reviews |  | Limit new starts | Delivery lead | 2026-09-25 | Release or outcome claim remains constrained | Atlas review 24 Sep | Watch | 2
Routine | Recovery | REC-01 | Connectivity and decision deterioration |  | Test the intervention, sustained change and displaced risk. | Programme manager | 2026-09-26 | Cutover slot and remaining cost exposure | Accepted production path and operator-led rehearsal | In progress | 308
Routine | Value | H-01 | Need reconfirmed 22 Sep; remaining cost open |  | Validate remaining cost | Sponsor | 2026-09-28 | Continuing value not fully evidenced | Atlas review 24 Sep | Within tolerance | 1
Routine | Readiness | H-06 | On-call access unverified |  | Rehearse operator access | Service owner | 2026-09-28 | Release or outcome claim remains constrained | R-04 | Watch | 6
Routine | Adoption | H-07 | Eligible-user denominator missing |  | Establish cohort | Business owner | 2026-09-30 | Release or outcome claim remains constrained | Atlas review 24 Sep | Watch | 7
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 13 - DATA & LISTS
Data, lists and calculation pool
Dropdown lists and the connected action pool. Do not clear formulas. All thresholds are configured on Project Setup.
Start here
Condition | Trajectory | Confidence | YesNo | Criticality | DecisionStatus | WorkStatus | ReadyStatus | Authority | Stage | Result | EvidenceBasis | Domain | Change | RESET | Controls
Within tolerance | Improving | High | Yes | Critical | Open | Open | Pass | Sponsor | Planned | Pass | Technical test only | Activity | Improving | Recognise | Value
Watch | Stable | Medium | No | High | Deferred | In progress | Gap | Steering | In progress | Gap | Operator demonstration | Output | Flat | Establish Reality | Flow
Intervention required | Deteriorating | Low |  | Normal | Decided | Closed | Unknown | PM | Acceptance queue | Unknown | Mixed evidence | Verified capability | Worsening | Surface Causes | Dependencies
Unknown | Unclear |  |  |  | Rejected |  | Not applicable | Specialist | Accepted |  | Not assessed | Readiness | Unknown | Execute Interventions | Decisions
[5 empty] | Superseded | [6 empty] | Adoption |  | Test Recovery | Assurance
[12 empty] | Realised value |  |  | Readiness
Adoption
Source / boundary | Detail
Publication | Karim Gaber Saleh. The Delivery Credibility Gap. Revised 24 Sep 2026. Chapters 3-20 and method note.
Toolkit | PM-Toolkit.pdf. T01-T09, 18 pages. Revised 24 Sep 2026.
Preserved rules | No composite health score. Evidence domains do not establish one another. Consumer evidence closes a dependency. Original actionable date survives deferrals.
Example extension | Atlas values taken from the toolkit. R-04, F-01, CAP-01, B-01, M-01, historical snapshots and local thresholds are explicit illustrative extensions.
Date reconciliation | DEP-07 is due 25 Sep. The workbook does not repeat the toolkit steering example wording overdue at 24 Sep. Missed prior commitments remain two.
Capacity and ranking | Attention ordering uses priority labels, deadline and source-row tie-break. The numeric sort key is administrative, never a project-health measure.
Limitations | No model validation or automatic release approval. Verify exception authority and scope. History is a manual value snapshot.
[16 empty] | Priority | Control | Source ID | Issue | Trigger | Next action | Owner | Due date | Consequence | Evidence required | Status | Source reference | Sort key | Critical key | Evidence key | Readiness key | Upcoming key | Steering key | Dependency key | Attention count
[16 empty] | Routine | Value | H-01 | Need reconfirmed 22 Sep; remaining cost open |  | Validate remaining cost | Sponsor | 2026-09-28 | Continuing value not fully evidenced | Atlas review 24 Sep | Within tolerance | 03 - HEALTH REVIEW row 9 | 346293030 | 999999999999 | 999999999999 | 999999999999 | 46293030 | 999999999999 | 999999999999 | 0
[16 empty] | Routine | Flow | H-02 | Acceptance queue growing across reviews |  | Limit new starts | Delivery lead | 2026-09-25 | Release or outcome claim remains constrained | Atlas review 24 Sep | Watch | 03 - HEALTH REVIEW row 10 | 346290031 | 999999999999 | 999999999999 | 999999999999 | 46290031 | 999999999999 | 999999999999 | 0
[16 empty] | Critical | Dependencies | H-03 | DEP-07 missed two commitments | INTERVENTION REQUIRED | Agree alternative sequence | Network owner | 2026-09-25 | Release or outcome claim remains constrained | DEP-07 | Intervention required | 03 - HEALTH REVIEW row 11 | 146290032 | 146290032 | 999999999999 | 999999999999 | 46290032 | 999999999999 | 999999999999 | 1
[16 empty] | Critical | Decisions | H-04 | D-014 actionable since 6 Sep | INTERVENTION REQUIRED | Select release option | Sponsor | 2026-09-25 | Release or outcome claim remains constrained | D-014 | Intervention required | 03 - HEALTH REVIEW row 12 | 146290033 | 146290033 | 999999999999 | 999999999999 | 46290033 | 999999999999 | 999999999999 | 1
[16 empty] | Critical | Assurance | H-05 | Production-scale recovery not demonstrated | EVIDENCE GAP BEFORE COMMITMENT | Commission representative rehearsal | Assurance lead | 2026-09-29 | Release or outcome claim remains constrained | CAP-01 | Unknown | 03 - HEALTH REVIEW row 13 | 146294034 | 146294034 | 146294034 | 999999999999 | 46294034 | 999999999999 | 999999999999 | 1
[16 empty] | Routine | Readiness | H-06 | On-call access unverified |  | Rehearse operator access | Service owner | 2026-09-28 | Release or outcome claim remains constrained | R-04 | Watch | 03 - HEALTH REVIEW row 14 | 346293035 | 999999999999 | 999999999999 | 999999999999 | 46293035 | 999999999999 | 999999999999 | 0
[16 empty] | Routine | Adoption | H-07 | Eligible-user denominator missing |  | Establish cohort | Business owner | 2026-09-30 | Release or outcome claim remains constrained | Atlas review 24 Sep | Watch | 03 - HEALTH REVIEW row 15 | 346295036 | 999999999999 | 346295036 | 999999999999 | 46295036 | 999999999999 | 999999999999 | 0
[16 empty] | Critical | Decisions | D-014 | Full release or smaller migration wave | THRESHOLD EXCEEDED ESCALATION REQUIRED APPROACHING DEADLINE LINKED DEPENDENCY UNRESOLVED | Escalate to named authority. Preserve original actionable date. | Sponsor | 2026-09-25 | Cutover booking and supplier slot exposed | Accepted connectivity and representative recovery evidence | Open | 04 - DECISION LOG row 9 | 146290037 | 146290037 | 999999999999 | 999999999999 | 46290037 | 146290037 | 999999999999 | 1
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Critical | Dependencies | DEP-07 | Cloud pilot network connectivity | REPEATED MISSED COMMITMENT LOW-CONFIDENCE FORECAST CONSUMER ACCEPTANCE MISSING | Review eliminate / decouple options before accepting another forecast. | Network owner | 2026-09-25 | Pilot production path cannot be accepted | Consumer witnesses production-path test | Unresolved | 05 - DEPENDENCIES row 9 | 146290087 | 146290087 | 999999999999 | 999999999999 | 46290087 | 999999999999 | 146290087 | 1
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Review | Flow | F-01 | Production-path acceptance | BLOCKER AGE THRESHOLD REPEATED MILESTONE MOVEMENT | Resolve the constraint and shorten the next evidence loop. | Network owner | 2026-09-25 | Release evidence remains unavailable | Witnessed routing and failover tests | Acceptance queue | 06 - FLOW row 9 | 246290137 | 999999999999 | 999999999999 | 999999999999 | 46290137 | 999999999999 | 999999999999 | 1
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Critical | Assurance | CAP-01 | Atlas pilot recovery / release candidate 3 | REPRESENTATIVE CAPABILITY NOT VERIFIED | Commission targeted evidence before the commitment date. | Assurance lead | 2026-09-29 | Release recovery claim unsupported at production scale | Production-path rehearsal with receiving operator | In progress | 07 - EVIDENCE & ASSURANCE row 9 | 146294187 | 146294187 | 146294187 | 999999999999 | 46294187 | 999999999999 | 999999999999 | 1
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Routine | Readiness | R-01 | Service ownership |  |  | Service owner | 2026-09-28 | Receiving team needs operational evidence | Scope and boundaries accepted | Pass | 08 - READINESS row 9 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 46293237 | 999999999999 | 999999999999 | 0
[16 empty] | Review | Readiness | R-02 | Observability | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 10 | 246293238 | 999999999999 | 999999999999 | 999999999999 | 46293238 | 999999999999 | 999999999999 | 1
[16 empty] | Routine | Readiness | R-03 | Support and service desk |  |  | Service owner | 2026-09-28 | Receiving team needs operational evidence | Representative ticket routing tested | Pass | 08 - READINESS row 11 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 46293239 | 999999999999 | 999999999999 | 0
[16 empty] | Critical | Readiness | R-04 | Access and on-call readiness | RELEASE BLOCKER LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Access owner | 2026-09-28 | Operators cannot demonstrate privileged access |  | Gap | 08 - READINESS row 12 | 146293240 | 146293240 | 999999999999 | 146293240 | 46293240 | 999999999999 | 999999999999 | 1
[16 empty] | Critical | Readiness | R-05 | Recovery and data integrity | RELEASE BLOCKER READINESS UNKNOWN LINKED DEPENDENCY UNRESOLVED | Hold release or obtain explicit authorised risk acceptance. | Assurance lead | 2026-09-29 | Recovery at production scale not demonstrated |  | Unknown | 08 - READINESS row 13 | 146294241 | 146294241 | 999999999999 | 146294241 | 46294241 | 999999999999 | 999999999999 | 1
[16 empty] | Review | Readiness | R-06 | Security | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 14 | 246293242 | 999999999999 | 999999999999 | 999999999999 | 46293242 | 999999999999 | 999999999999 | 1
[16 empty] | Review | Readiness | R-07 | Documentation | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 15 | 246293243 | 999999999999 | 999999999999 | 999999999999 | 46293243 | 999999999999 | 999999999999 | 1
[16 empty] | Routine | Readiness | R-08 | Supplier support |  |  | Service owner | 2026-09-28 | Receiving team needs operational evidence | Support hours and escalation confirmed | Pass | 08 - READINESS row 16 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 46293244 | 999999999999 | 999999999999 | 0
[16 empty] | Review | Readiness | R-09 | Training | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-28 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 17 | 246293245 | 999999999999 | 999999999999 | 999999999999 | 46293245 | 999999999999 | 999999999999 | 1
[16 empty] | Review | Readiness | R-10 | Incident response | READINESS UNKNOWN | Demonstrate the operator task and record current evidence. | Service owner | 2026-09-29 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 18 | 246294246 | 999999999999 | 999999999999 | 999999999999 | 46294246 | 999999999999 | 999999999999 | 1
[16 empty] | Critical | Readiness | R-11 | Cutover | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 19 | 146294247 | 146294247 | 999999999999 | 146294247 | 46294247 | 999999999999 | 999999999999 | 1
[16 empty] | Critical | Readiness | R-12 | Rollback | RELEASE BLOCKER READINESS UNKNOWN | Hold release or obtain explicit authorised risk acceptance. | Service owner | 2026-09-29 | Receiving team needs operational evidence |  | Unknown | 08 - READINESS row 20 | 146294248 | 146294248 | 999999999999 | 146294248 | 46294248 | 999999999999 | 999999999999 | 1
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Review | Adoption | B-01 | Reduce manual recovery coordination | DENOMINATOR MISSING OR ZERO NO BASELINE HANDOVER NOT RECORDED | Define eligible cohort before reporting adoption percentage. | Service owner | 2026-09-29 | Outcome claim cannot yet be supported | Comparable operator-led exercise with defined eligible cohort | In progress | 09 - ADOPTION & BENEFITS row 9 | 246294287 | 999999999999 | 246294287 | 999999999999 | 46294287 | 999999999999 | 999999999999 | 1
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Routine | Recovery | REC-01 | Connectivity and decision deterioration |  | Test the intervention, sustained change and displaced risk. | Programme manager | 2026-09-26 | Cutover slot and remaining cost exposure | Accepted production path and operator-led rehearsal | In progress | 10 - RECOVERY row 9 | 346291337 | 999999999999 | 999999999999 | 999999999999 | 46291337 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[16 empty] | Routine | AI delegation | AI-01 | Draft weekly migration status |  |  | Programme manager | 2026-09-30 | Incorrect evidence could mislead release decision | Source version and date for every material statement | In progress | 15 - AI DELEGATION row 9 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 46295387 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0
[28 empty] | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 999999999999 | 0

## 14 - REVIEW HISTORY
Review history
Before updating Health Review, append a dated value-only snapshot. Never paste formulas here. Matching needs one record per date and control.
Start here
Review date | Control | Condition | Trajectory | Confidence | Intervention | Owner | Due date | Observed effect | Effect evidence
2026-09-17 | Value | Within tolerance | Stable | Medium | Review evidence | Sponsor | 2026-09-24 | Effect not yet established | Illustrative historical review extension
2026-09-17 | Flow | Watch | Deteriorating | Medium | Add build capacity | Delivery lead | 2026-09-24 | Acceptance waiting did not improve | Illustrative historical review extension
2026-09-17 | Dependencies | Watch | Stable | Medium | Review evidence | Network owner | 2026-09-24 | Effect not yet established | Illustrative historical review extension
2026-09-17 | Decisions | Watch | Stable | Medium | Review evidence | Sponsor | 2026-09-24 | Effect not yet established | Illustrative historical review extension
2026-09-17 | Assurance | Watch | Stable | Low | Review evidence | Assurance lead | 2026-09-24 | Effect not yet established | Illustrative historical review extension
2026-09-17 | Readiness | Watch | Stable | Medium | Review evidence | Service owner | 2026-09-24 | Effect not yet established | Illustrative historical review extension
2026-09-17 | Adoption | Watch | Stable | Low | Review evidence | Business owner | 2026-09-24 | Effect not yet established | Illustrative historical review extension

## 15 - AI DELEGATION
AI delegation
Bound the task, data access and review. No automatic risk acceptance, executive communication or commercial commitment.
Start here | [9 empty] | Rows missing an ID: 0
ID | Use case | Status | Owner | Due date | Priority | Flags | Suggested action | Consequence | Evidence required | Permitted work | Prohibited action | Approved environment | Provenance requirement | Human reviewer | Quality checks | Output destination | Approval boundary | Pilot measure | Stop condition | Fallback | Next review
AI-01 | Draft weekly migration status | In progress | Programme manager | 2026-09-30 | Routine |  |  | Incorrect evidence could mislead release decision | Source version and date for every material statement | Summarise approved updates and flag contradictions | No sending, record changes, risk acceptance or date commitments | Approved project workspace. Redact unnecessary personal data | Preserve unknowns and link each claim | Programme manager | Verify dates, owners, commitments and qualifications | Internal draft | Human verifies and sends through normal route | Total preparation plus review effort and correction rate | Stop on fabricated evidence | Manual drafting and incident record | 2026-09-30